## DTT Test Hour Log
Instruction: Fill in the number of hours that were required to complete the test. Please include every step you took during development and include a detailed description of every step. Explain what problems you encountered, why you made certain decisions or applied specific techniques. We prefer quality over quantity so take your time with the test and the log. If external sources where used as reference, please mention them in the description
Subject | Amount of hours | Date | Description | Bonus
Project setup + environment check | 2.5 | 2026-01-23 | Opened the provided PHP skeleton and configured local environment. Also checked the project structure and had some issues with my XAMPP and phpMyAdmin user accounts not working. Watched some videos and read some tutorials on postman to properly understand how to use it.
Database setup + schema verification | 1.5 | 2026-01-23 | Set up db credentials in the config file and tested to see if the connection works. Added required tables to DB. I also double checked all expected relations.
Implement GET all facilities (+ related objects) | 1.5 | 2026-01-24 | I built GET /facilities to return facilities including nested location object and an array of related tags. Encountered an error where executeQuery() returned a boolean, causing fetchAll() to be called on a bool. Tried fixing it myself but couldn’t so I used Ai to solve and learn from my issue. Added separate query per facility to load tags (N+1 approach) | x
Implement GET single facility (by id) | 2 | 2026-01-24 | I Built GET /facilities/{id} to return one facility including nested location and tags. And I also added a 404 not found if the searched facility doesn’t exist. And made sure it worked using postman.
Fix JSON formatting issues for tags | 0.5 | 2026-01-24 | I also noticed that tag results had duplicated numeric keys and the root cause of it was PDO default fetch mode returned both numeric + associative keys. So I fixed it by doing some research and simply setting PDO fetch mode to "PDO::FETCH_ASSOC" globally so that the JSON output stays consistent and it just seemed cleaner.
Implement POST create facility (+ tags + pivot) | 2.5 | 2026-01-25 | I built POST facilities that supports JSON body and form data. And importantly I added safety checks that ensures location_id exists before inserting to prevent errors. And I implemented "getOrCreateTagId()" to reuse tags with unique name logic.
Implement PUT update facility (+ sync tags) | 2.5 | 2026-01-26 | Added PUT facilities id to update one or multiple areas (name, location_id and tags). Added validation that returns an error if no fields were added and it also validates that the location exists when updating location id to prevent empty name updates. I also added a tag "sync" that ensures when a facility is updated its tag relationships are fully replaced with the provided list, keeping the data consistent
Implement DELETE facility (+ pivot cleanup) | 1 | 2026-01-26 | Built DELETE facilties/id using transaction to ensure that multi step operations such as creating, updating, or deleting facilities and their tag relations are executed atomically, preventing partial updates and maintaining data consistency. Deleted pivot rows first from facility tag to avoid FK constraint issues then deleted facility. Also returned JSON success response and verified the facility was removed by calling GET after its been deleted.
Implement Search / filtering (compound + partial match) | 1.5 | 2026-01-26 | I built "GET /facilities/search?name=...&city=...&tag=…" that supports partial matches using "LIKE" and multiple parameters. I also used "LEFT JOIN" to tag tables so you could search by name or city and still get a facilities returned even if no tags. Required atleast one query parameter to avoid accidental "return everything"
Route debugging + Postman collection finalization | 2 | 2026-01-26 | Started having issues with postman so I had to change the base url to include /public so that the routes resolve correctly. I also updated the endpoints so match the implemented REST routes "/facilities, /facilities/{id}, /facilities/search". Also added request bodies for POST/PUT, then re-exported the updated collection so that it matches what was asked of me to submit and matches the working end points. Then I tested to see if all requests run well using baseurl.
Code quality + PDO hardening | 1 | 2026-01-26 | I wanted to improve the DB wrapper connection so I enabled "PDO::ATTR_ERRMODE => PDO::ERRMODE_EXCEPTION, PDO::ATTR_DEFAULT_FETCH_MODE => PDO::FETCH_ASSOC and PDO::ATTR_EMULATE_PREPARES => false" so that I could improve error visibility , gives consistent JSON output and makes sure my prepared statements behave securely. I removed bloat comments that I placed to remember little things.
External sources used |  |  | PHP Manual (for attrributes like ERRMODE / FETCH_ASSOC), Postman Docs (variables like {{baseUrl}}, exporting/importing collections), bramus/router docs/examples (route patterns and controller method mapping) and AI
Total amount of hours | 18.5